## Cutover Checklist
Phase | # | Task | Owner Team | Supporting Teams | Tool(s) | Dependencies | Status
PRE | 1 | Freeze Oracle DDL changes for cutover window | DBA | AppDev | - | Change freeze approved by AppDev & DataWarehouse | Not Started
PRE | 2 | Final ora2pg schema export validated against production Oracle DDL | DBA | ETL | ora2pg | DDL freeze in effect | Not Started
PRE | 3 | Striim replication topology (OLTP Oracle -> Postgres) validated end-to-end in staging | ETL | DBA | Striim | Target Postgres schema deployed | Not Started
PRE | 4 | Resolve '' vs NULL collapsing defect in Striim A->B job | ETL | DataWarehouse | Striim | Root cause identified in staging tests | Not Started
PRE | 5 | JSON/XML/UDT CDC gap mitigation finalized (fallback method scoped per table) | ETL | DBA | Striim | List of affected tables confirmed by DBA | Not Started
PRE | 6 | Azure Data Factory pipelines (Postgres OLTP -> OLAP) validated against staging Postgres | DataWarehouse | ETL | Azure Data Factory | Striim staging replication stable | Not Started
PRE | 7 | Row-count & checksum reconciliation scripts built and dry-run in staging | DataWarehouse | DBA | - | Staging data fully replicated | Not Started
PRE | 8 | SSRS/PBIRS reports pointed at staging Postgres and validated for output parity | Reporting | DataWarehouse | SSRS/PBIRS | ADF pipelines validated in staging | Not Started
PRE | 9 | Application connection strings / config staged (not yet switched) for Postgres target | AppDev | DBA | - | Target Postgres provisioned & sized for prod load | Not Started
PRE | 10 | Rollback plan documented and dry-run tested (revert to Oracle path) | DBA | AppDev, ETL | Striim | Staging cutover rehearsal completed | Not Started
PRE | 11 | [UAT LESSON] Validate all Postgres sequences created and aligned to correct start values (nextval > max existing PK) | DBA | ETL | ora2pg | UAT cutover found sequence mismatches | Not Started
PRE | 12 | [UAT LESSON] Script sequence re-sync step (setval to max(id)+1) for every migrated table with a sequence-backed PK | DBA | ETL | ora2pg | Sequence audit from UAT defect list | Not Started
PRE | 13 | [UAT LESSON] Full grants/permissions matrix documented per schema/table for AppDev, ETL, DataWarehouse, Reporting roles | DBA | AppDev, ETL, DataWarehouse, Reporting | - | UAT cutover found missing table permissions | Not Started
PRE | 14 | [UAT LESSON] Grants/permissions script tested in staging and confirmed idempotent (safe to re-run during cutover) | DBA | - | - | Permissions matrix documented | Not Started
PRE | 15 | Go/No-Go criteria and runbook reviewed & signed off by all teams | DBA | AppDev, ETL, DataWarehouse, Reporting | - | All PRE items above complete, including UAT lesson remediations | Not Started
PRE | 16 | Maintenance window scheduled and communicated to all stakeholders | AppDev | DBA, ETL, DataWarehouse, Reporting | - | Go/No-Go sign-off | Not Started
DURING | 1 | Set Oracle source to read-only lockdown | DBA | AppDev | - | Maintenance window start | Not Started
DURING | 2 | Capture final delta sync point (SCN / LSN) for cutover | DBA | ETL | Striim | Oracle read-only lockdown confirmed | Not Started
DURING | 3 | Run final Striim delta sync Oracle -> Postgres OLTP | ETL | DBA | Striim | Final sync point captured | Not Started
DURING | 4 | Run final ADF pipeline sync Postgres OLTP -> OLAP | DataWarehouse | ETL | Azure Data Factory | Striim final sync completed & verified | Not Started
DURING | 5 | [UAT LESSON] Execute sequence re-sync script on all migrated tables and verify nextval values | DBA | ETL | ora2pg | Final ADF sync completed | Not Started
DURING | 6 | [UAT LESSON] Apply and verify full grants/permissions script on production schema (AppDev, ETL, DataWarehouse, Reporting roles) | DBA | AppDev, ETL, DataWarehouse, Reporting | - | Sequence re-sync verified | Not Started
DURING | 7 | Execute row-count & checksum reconciliation (source vs target) | DataWarehouse | DBA, ETL | - | Final ADF sync completed | Not Started
DURING | 8 | Verify '' vs NULL fidelity on reconciled tables | DataWarehouse | ETL | - | Reconciliation scripts executed | Not Started
DURING | 9 | Switch application connection strings / DNS to Postgres target | AppDev | DBA | - | Reconciliation passed | Not Started
DURING | 10 | Repoint SSRS/PBIRS report data sources to production Postgres | Reporting | DataWarehouse | SSRS/PBIRS | Reconciliation passed | Not Started
DURING | 11 | Go/No-Go checkpoint before releasing traffic to Postgres | DBA | AppDev, ETL, DataWarehouse, Reporting | - | All prior DURING steps green | Not Started
DURING | 12 | Release application traffic to Postgres target | AppDev | DBA | - | Go/No-Go checkpoint passed | Not Started
POST | 1 | Application smoke tests against production Postgres | AppDev | DBA | - | Traffic released | Not Started
POST | 2 | [UAT LESSON] Verify no sequence-related insert failures (PK collisions) across all migrated tables under real traffic | DBA | AppDev | - | Smoke tests passed | Not Started
POST | 3 | [UAT LESSON] Verify no permission-denied errors across AppDev/ETL/DataWarehouse/Reporting workloads under real traffic | DBA | AppDev, ETL, DataWarehouse, Reporting | - | Smoke tests passed | Not Started
POST | 4 | Validate SSRS/PBIRS report output parity in production | Reporting | DataWarehouse | SSRS/PBIRS | Traffic released | Not Started
POST | 5 | Monitor Striim/ADF pipeline health and lag on production load | ETL | DataWarehouse | Striim, Azure Data Factory | Traffic released | Not Started
POST | 6 | Monitor Postgres performance (query latency, connections, errors) | DBA | AppDev | - | Traffic released | Not Started
POST | 7 | Final signed-off reconciliation report circulated to all teams | DataWarehouse | DBA, ETL | - | Smoke tests passed | Not Started
POST | 8 | Hypercare period staffing/on-call confirmed for all teams | DBA | AppDev, ETL, DataWarehouse, Reporting | - | Traffic released | Not Started
POST | 9 | Oracle source retained in read-only mode for validation window (no decommission yet) | DBA | AppDev | - | Hypercare window defined | Not Started
POST | 10 | Post-cutover retro and lessons-learned session scheduled | DBA | AppDev, ETL, DataWarehouse, Reporting | - | Hypercare window complete | Not Started
POST | 11 | Oracle decommission plan approved and scheduled | DBA | AppDev, DataWarehouse | - | Validation window passed with sign-off | Not Started

## Legend
Column | Meaning
Phase | PRE = before cutover window, DURING = within maintenance window, POST = after traffic cutover
Owner Team | Team accountable for completing/signing off the task
Supporting Teams | Teams that must be consulted or involved but are not accountable
Tool(s) | Primary tool(s) used to execute the task
Dependencies | What must be true/complete before this task can start
Status | Update via dropdown: Not Started / In Progress / Blocked / Complete
Teams | AppDev, DBA, ETL, DataWarehouse, Reporting
Tools | Striim, Azure Data Factory, SSRS/PBIRS, ora2pg
[UAT LESSON] tag | Added after UAT cutover (run prior day) surfaced sequence mismatches and missing table permissions as the two main defect categories